TEAM CHARTER

Exploring E. coli Risk Patterns Using Rainfall and Environmental Data

Client: Water Services Authority – Taumata Arowai

University of Canterbury – Virtual Internship 2026

How to use this charter: Blue italic text marks decisions for the team to confirm at the Phase 0 kickoff meeting. Fill those in together, then have every member sign Section 12. Revisit it if the project scope or team changes.

# 1. Project Overview

| Project name | Exploring E. coli Risk Patterns Using Rainfall and Environmental Data |
| --- | --- |
| Client | Water Services Authority – Taumata Arowai (taumataarowai.govt.nz) |
| Project type | Proof-of-concept data analysis (not a complete predictive tool) |
| Duration | Approx. 4 weeks – proposed 18 June to 17 July 2026 |
| Deliverable 1 | Team-written report, 2,500–3,000 words including citations |
| Deliverable 2 | 10-minute team presentation |
| Submission dates | [To be confirmed with the Program Organizer / Mentor] |

# 2. Team Purpose & Shared Goals

Our purpose is to explore whether simple data analysis can reveal patterns in E. coli risk following rainfall events, and to communicate our findings clearly to the client. As a team we commit to the following shared goals:

- Deliver both a high-quality report and presentation on time and within scope.

- Produce honest, defensible analysis – we will be clear about what the data can and cannot show.

- Contribute equitably, so every member learns and the workload is shared fairly.

- Score well against all six rubric criteria (see Section 11).

- Work professionally and supportively, treating this as a real client engagement.

# 3. Team Members & Roles

Five members, each leading one area. Leads coordinate their area; everyone contributes to the report and presentation.

| Member (name) | Role | Contact (email / phone) |
| --- | --- | --- |
| Ahmed Masoom | Project Lead | ama778@uclive.ac.nz |
| Hanna Hautea | Visualisation / GIS Lead | hanapatriciahautea@gmail.com |
| Rupika | Analysis Lead | [email] |
| Rex | Data Lead | [email] |
| Max | Report & Comms Lead | [email] |

# 4. Roles & Responsibilities

Project Lead (Ahmed):

- Owns the timeline and ClickUp board; keeps the team on track to deadlines.

- Runs meetings, records decisions, and is the main point of contact.

- Coordinates final submission and drafts the limitations/recommendations section.

Data Lead:

- Sources rainfall, E. coli and environmental datasets; documents licences.

- Cleans, structures and joins the data into an analysis-ready set.

Analysis Lead:

- Runs the exploratory analysis (rainfall vs E. coli, location, features).

- Designs, builds and tests the low/medium/high risk score.

Visualisation / GIS Lead:

- Creates charts, tables, maps and the dashboard-style summary.

- Ensures visuals are clear, accurate and presentation-ready.

Report & Comms Lead:

- Owns report structure, formatting, citations (Zotero) and word count.

- Coordinates the slide deck and presentation logistics.

All members:

- Attend meetings, update ClickUp tasks, contribute to writing and rehearse the talk.

# 5. Communication Plan

| Channel | Used for | Expected response time |
| --- | --- | --- |
| WhatsApp | Quick questions, day-to-day chat | Within 1 hours on weekdays |
| Email | Formal / external comms tutor | Within 24 hours |
| ClickUp comments | Task-specific discussion & decisions | When working on the task |
| Zoom | Team meetings | Confirm/declines participation 24 Hours before the meeting |
| OneDrive | Files, datasets, report drafts | N/A |

Norm: if you are unavailable or cannot meet a deadline, tell the team as early as possible.

# 6. Meeting Cadence

- Weekly Internal team meeting: Every Friday at 8:30 pm, approx. 45 minutes for reviewing progress, planning the week, unblocking the issues.

- Weekly meeting with Mentor: Ever Sunday, approximately 1 hour for reviewing the progress

- Short mid-week check-in: Async update in WhatsApp / ClickUp

- Each meeting has a brief agenda; the Project Lead records key decisions and action items in ClickUp.

- Ad-hoc working sessions as needed near deliverable dates.

# 7. Decision-Making

- Routine decisions are made by the relevant role lead.

- Decisions affecting scope, methods or deliverables are made by the team, aiming for consensus.

- If consensus cannot be reached, we decide by majority vote; the Project Lead breaks a tie.

- All significant decisions are recorded (in ClickUp or meeting notes) so they are not relitigated.

# 8. Ways of Working – Team Norms

- Treat each other with respect; everyone’s input is valued.

- Keep tasks in ClickUp up to date – status, blockers and links to outputs.

- Deliver your tasks by the agreed date, or flag early if you cannot.

- Give feedback on the work, not the person; assume good intent.

- Version control: save files in the shared drive with clear names; avoid duplicate copies.

- Reference everything – capture sources as you go for citations.

# 9. Task & Project Management

We manage the project in ClickUp using the imported plan (8 phases, 49 subtasks). Conventions:

- Every task has an owner, a due date and a status (To Do / In Progress / In Review / On Hold / Done).

- Update your task status before each meeting.

- Use the Board view for standups, Gantt/Timeline to watch the critical path, and Calendar for the week.

- Raise blockers as ClickUp comments and @mention the people involved.

# 10. Accountability & Deadlines

- Internal deadlines are set a few days before any official due date to allow review and buffer.

- If a member repeatedly misses commitments, the team discusses it openly and supportively first.

- Persistent issues are escalated to the program tutor/coordinator as a last resort.

- We track contribution fairly, so peer/teamwork assessment reflects reality.

# 11. Quality Standards – Definition of Done

We will be assessed against the brief’s six rubric criteria. A deliverable is “done” when it meets these:

| Rubric criterion | What “good” looks like for us |
| --- | --- |
| Written Communication / Structure | Clear, well-organised report within 2,500–3,000 words, proofread. |
| Getting Information | Relevant, credible data sources identified and documented. |
| Analysing Data & Information | Sound, reproducible analysis; conclusions supported by evidence. |
| Critical Thinking | Honest about limitations; thoughtful recommendations and next steps. |
| Teamwork | Equitable contribution; decisions and workload shared. |
| Presentation Skills | Clear, well-rehearsed 10-minute talk; everyone presents. |

Every report section and the deck get a peer review before submission.

# 12. Conflict Resolution

- Raise the issue early and directly with the people involved, in private and respectfully.

- If unresolved, bring it to the full team to discuss and agree a way forward.

- If still unresolved, the Project Lead facilitates a decision per Section 7.

- As a last resort, escalate to the program tutor/coordinator.

# 13. Risks & Contingencies

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Data hard to find or access | Delays analysis | Start sourcing in week 1; have a backup catchment/sample dataset. |
| A member unavailable / drops out | Workload imbalance | Cross-share knowledge; document work in ClickUp; redistribute early. |
| Report over word limit / late | Marks lost | Word-count check task. |

# 14. Agreement & Sign-Off

By signing below, each member agrees to uphold this charter for the duration of the project.

| Name | Signature | Date |
| --- | --- | --- |